## Sheet1
SL.NO | TASKS | DIFFICULTY LEVEL | DEPENDENCIES | ESTIMATED START DATE | ACTUAL START DATE | ESTIMATED END DATE | ACTUAL END DATE | ASSIGNED TO
1 | Create Requirement Specification Document |  | None | 2019-01-30 | 30-02-2019 | 2019-02-04 | 2019-02-06 | Team 1
2 | Create Functional and Technical Architecture |  | Explore on frameworks required and compliant with oher frameworks used. | 2019-02-04 | 2019-02-04 | 2019-02-06 | 2019-02-07 | Team 1
3 | Download and setup frameworks required |  |  | 2019-02-04 | 2019-02-04 | 2019-02-05 | 2019-02-05 | Team 1
SonarQube setup for Server Side
4 | Explore external APIs for Maps
5 | Explore external APIs for Transport
6 | Explore external APIs for Preferences
Explore Fault Tolerance Mechanisms
7 | Routing Algorithm and Pseudocode
8 | User Management Service - Database Setup
9 | User Management Service - Client Communication
10 | User Management Service - Interface for Route Ranker Service
Implement Hystrix for Fault Tolerance
11 | Route Ranker Service- Fetching Geocoordinates
12 | Route Ranker Service- Maps API call (Only Public Transit)
13 | Route Ranker Service - 2 Mode Routing Logic
14 | Route Ranker Service - 3 Mode Routing Logic - Insert Dublin Bikes
RRS- Rail and Bus Integration
15 | RRS- Interface with User Management Service
16 | RRS- Interface with API Handler Service
17 | RRS- Fetch User Preferences (Per Client) from User Management Service
RRS- Fetch Real-Time Data (e.g. weather, pollution, etc.) from API Handler Service
Simulating backup preference data (e.g. weather, pollution, etc.)
API Handler Database Setup
API Handler - Calls to fetch real time data from external APIs
Preference Metrics Calculation
Assign Route Scores based on Promoting Sustainability
Reassign Route Scores based on Weather Preferences
Sorting Route Results
Creating final Routes JSON
Send Final Routes JSON to Client
Reassign Route Scores based on Pollution Preferences
Fetch Route Congestion Data
Reassign Route Scores based on Traffic Preferences
AWS RDS Database Setup
Docker Connection Setup
Docker Containers Setup
Service Deployment on AWS Instance
Enable admin access for emergency notification
Identify Active Client's Routes affected by emergency
Find unaffected routes from a client's routes JSON
Notification Pushing Service to Client
Return New Routes JSON to Affected Client
Edge Implementation